***Activity Proposal SOP***

|  |  |
| --- | --- |
| Procedure | Responsible parties |
| AS | RF | MST | SL |
| Having a thought to organize an activity. |  |  |  | ✓ |
| Preparing* Planning and writing the proposal at least 21 days before the activity date;
* A proposal should include the title of the activity, date, time, location, organizers with contacts (email, phone number, student ID number) , estimated number of participants, objectives, description, and budget;
* The student leaders should check the CKPC Event Page (https://ckpc.rc.umac.mo/events/) for potential time conflict with other CKPC activities

Note: For the details of proposal writing, please refer to the proposal template. |  |  |  | ✓ |
| Proposal checking by RFs* Student leaders should submit the proposal to RFs at least 16 days before the activity date;
* Please check text spelling and grammar before submitting the proposal;
* When student leaders send the email, please name the email title as “ proposal\_(activity title)” and c.c. other organizers;
* RFs will forward the proposal to financial staff and c.c. the student leader (organizer) by email ;
* If there are contents that need modification, RFs will send the recommended changes to student leaders. Student leaders should follow RFs’ recommendations to revise the proposal.
* Student leaders should check the progress if there is no response two working days after submitting the email.
 |  | ✓ |  | ✓ |
| Budget checking by financial staff* Financial staff will forward the proposal to Master if the fund is available ;
* If it is not available, financial staff will contact the organizers and discuss the budget issue. The organizers may either revise the proposal or cancel the activity.
* Student leaders should check the progress if there is no response two working days after RFs passing the proposal to financial staff;
 | ✓ |  |  | ✓ |
| Approval by Master* Staff will notify the organizers about the result from the Master;
* Student leaders should check the progress if there is no final response a week before the activity date;
 | ✓ |  | ✓ | ✓ |
| After the approval by the Master, student leaders can start to prepare for the activity.  |  |  |  | ✓ |

Note:

1) AS: admin staff; SL: student leaders; MST: Master; RF: Resident Fellow